## Project Plan_ONW Mexico
Steps# | Lite Integration - Tasks & Activities | Description | Assigned To | Duration | Start Date | End Date | % Complete | Status | Comments
1 | Kick off and Project Initiation |  |  | 1D
2 | Requirements |  |  | 5D
2.1 | Functional Due Diligence (Cash + Collections) | Finalize Oprations strategy and the servicing scope | Genpact
2.2 | IT Due Diligence | Finalise GENAISYS configuration based on business needs | Genpact IT
2.3 | Races Requirements | GENAISYS configuration to be setup at Races end (BCO+IC) | Races IT
2.4 | FDL Requirements | Information on the RACES OU to be added into FDL template | FDL team
3 | Design and Build (Pre-requisite to SIT) |  |  | 5D
3.1 | Setups at GENAISYS | Configure and prep GENAISYS to perform testing | Genpact IT
3.2 | User readiness at RACES | Identify the cash applier, check if they have access to RACES test environment.
3.3 | SIT setups and data visibility at RACES | 1. Configure RACES with GENAISYS identifiers (IC+BCO) 2. Setup Receipts Methods in RACES 3. Availablity of Test data in RACES | Races IT
3.4 | Connectivity and setup between FDL and Races | Connectivity to exist between FDL and Races. Expected customer and invoice data to be available in FDL | FDL Team
3.4.1 | Point the FDL environment to RACES preferred test instance | FDL instance and Races instance to be decided and FDL instance points to Races instance (This needs a prior planning as FDL is extensively used by other Biz's) | HVR Team
3.4.2 | Modify in FDL the security for the GENAISYS interface | Optional step to check the instances are connected, essentially FDL to GENAISYS. To make sure that on sending data feed during testing, it doesn’t fail | FDL Team
3.4.3 | Mirror refresh for all modules including Receipts table | Information on additional Org Ids and timing to refresh Pre-requisite -> Data availability at RACES | FDL Team | [5 empty] | Staging layer refresh
3.4.4 | Model refresh for all modules including Receipts table | Final step to populate Model tables Pre-requisite -> Completion of Mirror refresh and data availability at RACES | FDL Team | [5 empty] | Model tables populated
3.5 | FDL interface setup with GENAISYS | Optional step to establish/check FDL instance connectivity with GENAISYS test SFTP server | Genpact IT
3.6 | Rifle shot test to confirm connectivity in the agreed environment for testing (FDL-> GENAISYS) | Optional step to check the instances are connected essentially FDL to GENAISYS. To make sure that on sending data feed during testing, it doesn’t fail | FDL Team, Genpact IT
3.7 | Identify Cash Applier & get required access to Races test environment | Users Readiness in RACES | Genpact Cash
3.8 | Prepare and plan Cash Application Testing
3.8.1 | Share Races OI Report | Races OI Report will serve as the starting point of preparation of test script for cash testing | Races IT
3.8.2 | Create required invoices, CNs as necessary to cover test scenarios | Extra open items to be created in Races to cover all Lite scenarios as suggested by GENAISYS Cash Lead | Races IT
3.8.3 | Prepare Cash Application scenario for Cash App Testing | Prepare cash test script | Genpact Cash
4 | Testing - SIT Execution |  |  | 5D
4.1 | Lite Integration Testing Day - 0
4.1.1 | FDL Refresh - SIT first load | Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
4.1.2 | Mirror refresh for all modules including Receipts table | Information on additional Org Ids and timing to refresh Pre-requisite -> Data availability at RACES | FDL Team | [5 empty] | Staging layer refresh
4.1.3 | Model refresh for all modules including Receipts table | Final step to populate Model tables Pre-requisite -> Completion of Mirror refresh and data availability at RACES | FDL Team | [5 empty] | Model tables populated
4.1.4 | FDL to send Customer & Invoice feed to GENAISYS | FDL to send the files to GENAISYS via SFTP | FDL Team
4.1.5 | GENAISYS to load the customer & invoice feed |  | Genpact IT
4.1.6 | Validation of customer & invoice feed in GENAISYS | Manual Recon between GENAISYS & RACES Customer Master & OI Report | Genpact
4.1.7 | Prepare Cash Test Scenarios for Day 1 & 2 | Update Cash Test scenarios with accurate Inv#, CN# and Customer# | Genpact Cash
4.2 | Lite Integration Testing Day - 1
4.2.1 | Cash Application Test at Races - Day 1 scenarios |  | Genpact Cash Applier
4.2.2 | FDL Refresh - SIT second load | Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
4.2.3 | Mirror refresh for all modules including Receipts table | Information on additional Org Ids and timing to refresh Pre-requisite -> Data availability at RACES | FDL Team | [5 empty] | Staging layer refresh
4.2.4 | Model refresh for all modules including Receipts table | Final step to populate Model tables Pre-requisite -> Completion of Mirror refresh and data availability at RACES | FDL Team | [5 empty] | Model tables populated
4.2.5 | FDL to send Customer & Invoice feed to GENAISYS | FDL to send the files to GENAISYS via SFTP | FDL Team
4.2.6 | GENAISYS to load the customer & invoice feed |  | Genpact IT
4.2.7 | Validation of customer & invoice feed in GENAISYS | 1. Manual Recon between GENAISYS & RACES Customer Master & OI Report 2. Validation of Cash App Testing Results | Genpact 1 - Collections 2 - Cash
4.3 | Lite Integration Testing Day - 2
4.3.1 | Cash Application Test at Races - Day 2 scenarios |  | Genpact Cash Applier
4.3.2 | FDL Refresh - SIT third load | Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
4.3.3 | Mirror refresh for all modules including Receipts table | Information on additional Org Ids and timing to refresh Pre-requisite -> Data availability at RACES | FDL Team
4.3.4 | Model refresh for all modules including Receipts table | Final step to populate Model tables Pre-requisite -> Completion of Mirror refresh and data availability at RACES | FDL Team
4.3.5 | FDL to send Customer & Invoice feed to GENAISYS | FDL to send the files to GENAISYS via SFTP | FDL Team
4.3.6 | GENAISYS to load the customer & invoice feed |  | Genpact IT
4.3.7 | Validation of customer & invoice feed in GENAISYS | 1. Manual Recon between GENAISYS & RACES Customer Master & OI Report 2. Validation of Cash App Testing Results | Genpact 1 - Collections 2 - Cash
4.4 | SIT Sign off |  | Genpact Races
5 | Design and Build (Pre-requisite to UAT) |  |  | 5D
5.1 | Setups at GENAISYS | Configure and prep GENAISYS to perform testing | Genpact IT
5.2 | User readiness at RACES | Identify the cash applier, check if they have access to RACES test environment.
5.3 | UAT setups and data visibility at RACES | 1. Configure RACES with GENAISYS identifiers (IC+BCO) 2. Setup Receipts Methods in RACES 3. Availablity of Test data in RACES | Races IT
5.4 | Connectivity and setup between FDL and Races | Connectivity to exist between FDL and Races. Expected customer and invoice data to be available in FDL | FDL Team
5.4.1 | Point the FDL environment to RACES preferred test instance | FDL instance and Races instance to be decided and FDL instance points to Races instance (This needs a prior planning as FDL is extensively used by other Biz's) | HVR Team
5.4.2 | Modify in FDL the security for the GENAISYS interface | Optional step to check the instances are connected, essentially FDL to GENAISYS. To make sure that on sending data feed during testing, it doesn’t fail | FDL Team
5.4.3 | Mirror refresh for all modules including Receipts table | Information on additional Org Ids and timing to refresh Pre-requisite -> Data availability at RACES | FDL Team | [5 empty] | Staging layer refresh
5.4.4 | Model refresh for all modules including Receipts table | Final step to populate Model tables Pre-requisite -> Completion of Mirror refresh and data availability at RACES | FDL Team | [5 empty] | Model tables populated
5.5 | FDL interface setup with GENAISYS | Optional step to establish/check FDL instance connectivity with GENAISYS test SFTP server | Genpact IT
5.6 | Rifle shot test to confirm connectivity in the agreed environment for testing (FDL-> GENAISYS) | Optional step to check the instances are connected essentially FDL to GENAISYS. To make sure that on sending data feed during testing, it doesn’t fail | FDL Team, Genpact IT
5.7 | Identify Cash Applier & get required access to Races test environment | Users Readiness in RACES | Genpact Cash
5.8 | Prepare and plan Cash Application Testing
5.8.1 | Share Races OI Report | Races OI Report will serve as the starting point of preparation of test script for cash testing | Races IT
5.8.2 | Create required invoices, CNs as necessary to cover test scenarios | Extra open items to be created in Races to cover all Lite scenarios as suggested by GENAISYS Cash Lead | Races IT
5.8.3 | Prepare Cash Application scenario for Cash App Testing | Prepare cash test script | Genpact Cash
6 | Testing - UAT Execution |  |  | 5D
6.1 | Lite Integration Testing Day - 0
6.1.1 | FDL Refresh - UAT first load | Refresh FDL mirror and model, all modules (incl. Receipts table)
6.1.2 | Mirror refresh for all modules including Receipts table | Information on additional Org Ids and timing to refresh Pre-requisite -> Data availability at RACES | FDL Team
6.1.3 | Model refresh for all modules including Receipts table | Final step to populate Model tables Pre-requisite -> Completion of Mirror refresh and data availability at RACES | FDL Team
6.1.4 | FDL to send Customer & Invoice feed to GENAISYS | FDL to send the files to GENAISYS via SFTP | FDL Team
6.1.5 | GENAISYS to load the customer & invoice feed |  | Genpact IT
6.1.6 | Validation of customer & invoice feed in GENAISYS | Manual Recon between GENAISYS & RACES Customer Master & OI Report | Genpact
6.1.7 | Prepare Cash Test Scenarios for Day 1 & 2 | Update Cash Test scenarios with accurate Inv#, CN# and Customer# | Genpact Cash
6.2 | Lite Integration Testing Day - 1
6.2.1 | Cash Application Test at Races - Day 1 scenarios |  | Genpact Cash Applier
6.2.2 | FDL Refresh - UAT second load | Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
6.2.3 | Mirror refresh for all modules including Receipts table | Information on additional Org Ids and timing to refresh Pre-requisite -> Data availability at RACES | FDL Team
6.2.4 | Model refresh for all modules including Receipts table | Final step to populate Model tables Pre-requisite -> Completion of Mirror refresh and data availability at RACES | FDL Team
6.2.5 | FDL to send Customer & Invoice feed to GENAISYS | FDL to send the files to GENAISYS via SFTP | FDL Team
6.2.6 | GENAISYS to load the customer & invoice feed |  | Genpact IT
6.2.7 | Validation of customer & invoice feed in GENAISYS | 1. Manual Recon between GENAISYS & RACES Customer Master & OI Report 2. Validation of Cash App Testing Results | Genpact 1 - Collections 2 - Cash
6.3 | Lite Integration Testing Day - 2
6.3.1 | Cash Application Test at Races - Day 2 scenarios |  | Genpact Cash Applier
6.3.2 | FDL Refresh - SIT third load | Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
6.3.3 | Mirror refresh for all modules including Receipts table | Information on additional Org Ids and timing to refresh Pre-requisite -> Data availability at RACES | FDL Team
6.3.4 | Model refresh for all modules including Receipts table | Final step to populate Model tables Pre-requisite -> Completion of Mirror refresh and data availability at RACES | FDL Team
6.3.5 | FDL to send Customer & Invoice feed to GENAISYS | FDL to send the files to GENAISYS via SFTP | FDL Team
6.3.6 | GENAISYS to load the customer & invoice feed |  | Genpact IT
6.3.7 | Validation of customer & invoice feed in GENAISYS | 1. Manual Recon between GENAISYS & RACES Customer Master & OI Report 2. Validation of Cash App Testing Results | Genpact 1 - Collections 2 - Cash
6.4 | UAT Sign off |  | Genpact Races
7 | Go-No Go Review |  | Genpact | 1D
8 | CCB Approval |  | Races IT | 1D
9 | Cutover |  |  | 5D
9.1 | Raise Races access for Cash Applier & Collector |  | Genpact
9.2 | Users Training for Cash Ops and Collections, if required |  | Genpact
9.3 | Setups at Races |  | Races IT
9.4 | Setups at FDL |  | FDL Team
9.5 | Setups at GENAISYS |  | Genpact IT
10 | Go - Live
11 | Deploy eReports & grant access to required users |  | Genpact IT | 10D
12 | Hypercare

## Sheet1
Ref | Activities | Status | Apr'21 |  |  |  | May'21
|  |  | 6-10 | 13-17 | 20-24 | 27-30 | 3-7 | 10-14 | 17-21 | 24-28
1 | List GENAISYS Activities | Completed
2 | List RACES Activities | Completed | bar: Apr'21 6-10 to Apr'21 13-17
3 | List FDL Activities | Completed | bar: Apr'21 13-17 to Apr'21 20-24
4 | Prepare draft version of project plan | Completed | bar: Apr'21 6-10 to Apr'21 20-24
5 | Consolidate and finalise the plan | In Progress | bar: Apr'21 27-30
6 | Review & final signoff by all stakeholders | Not Started | bar: Apr'21 27-30 to May'21 3-7
FDL - Helen
RACES - Jeanne Moore, Anett, Vish