## Sheet1
All | Progress | before | initiation | of | website | : | Daily updates.msg
Below | From | 2014-02-01 | To | 2018-03-01
SL NO | Solution | Contacted | Status | Person in Contact | GE DIV | Response | Reason
1 | WP | YES | Ongoing | AG Sharanabasav | GE Research | Negative | GE Research have support for Wp but they donot give support to GE REN. Gave contact of Rita Doshi (GE CORP)
2 | WP | YES | ENDED | Rita Doshi | GE Corp | Redirected | Redirected to Pankaj and Kirk Vantine
3 | WP | YES | ENDED | Kirk Vantine | GE Corp | HOLD | Hosting charge of 2.7k $ a month
4 | WP | YES | ENDED | Abir Majumdar | GE Power | Negative | Redirected to Ramesh Bikkani
5 | WP | YES | ENDED | Lee Cunningham | GE Power | Negative | GE Power installation of WordPress no longer maintained by him. Doesn’t know who maintains it now
https://blogs.gepower.com/
6 | WP | YES | No Response | Ramesh Bikkani | GE Power | NONE | No response
7 | WP | YES | ENDED | David Ensor | GE Aviation | Negative | GE Aviation istallation for WordPress can't support sites of GE REN. Can support if there is an Aviation employee taking ownership
https://blogs.aviation.ge.com/
8 | WP | YES | ENDED | Joshua Kephart | GE Aviation | Negative | Gave contact to David Ensor. No autobank user in Aviation/ Cant take ownership of REN project.
9 | WP | YES | Ongoing | AG Sharanabasav | GE Research | TBD | Gave contact of Bidar Gopinath(GE REN)-->Need help for permanent solution in form of WP installation for GE REN like all other divs, which can be used by all teams within GE REN
10 | WP | YES | ENDED | Devendra Kumar | GE REN | Ongoing | No installation for WP. Solution for Drupal sites
11 | WP+Drupal | YES | ENDED | Marco Buzzo | Baker Hughes | Negative | Drupal and Wordpress have been discontinued long time ago in Baker Hughes
12 | PREDIX | YES | Ongoing | Premadhas Murugesan | GE Digital | Negative | Very steep learning curve for web development and Predix, cannot be done single handedly in 3 months. Post that Predix solution will be much costlier than the cost that GE Corporate gave us for thir solution
Predix conversation link 1
Prexdix conversation link 2
13 | WP+Drupal | YES | Ongoing | Venkata Kakani | GE Digital | Redirected | Redirected to Kim White(GE Corporate)
14 | WP+Drupal | YES | No Response | Arvind Pasrija | GE REN | NONE | NONE
15 | WP inst. | YES | ENDED | Michael Breen | GE REN | HOLD | The cost of only associating CTO is 3k $. Issues of time and funding for starting the project on WP installation. Plus issues on who will maintain it .
Why no wp installation
16 | WP | YES | ENDED | Kim White | GE Corp | Positive | Proposed solution at cost of less than 1k $ a month, down from 2700 $
17 | SharePoint | YES | ENDED | Ipsita Ojha | GE Power | Positive | Adviced to try SharePoint
18 | SharePoint | YES | ENDED | Olivier Leprince | GE REN | Positive | Said that he maintains applications in GE REN and SharePoint is one of them, so we can proceed with it
19 | SharePoint | YES | Ongoing | Priscillia Buissiere | GE core & cyberT | Positive | SP as it comes in GE is a out of box version; meaning that we can have user collection level of permission and site can be configured with whats present by default and no updates in code can be made
SharePoint overview