## Sheet1
Make sure that the priorities are SMART - Specific, Measurable, Achievable, Realistic, Time-bound - https://corporatefinanceinstitute.com/resources/knowledge/other/smart-goal/#:~:text=SMART%20is%20an%20acronym%20that,Well%20defined%2C%20clear%2C%20and%20unambiguous
Build and implement website for cash automation
Description: Create a website for cash automation which will be a one stop place for all docs and tools related to cash automation process.
Pre1. Explore solutions available across GE. Pre2. Cost benefit of each solution. a. GE domain name. b. Internal hosting within GE. c. SSO integration. Pre3. Select suitable tech stack based on step 1,2. M1. Design of website. M2. Build of website. M3. Test and Deploy
Today%: 1. WordPress, Bench (Proceeding with WP, trial done for Bench) 2. Cost to be guided by Devendra for a, b, c. 3. WordPress( Subject to change ) 4. 30% (Rough design done, reviewed by team) 5. 20% (Rough idea of contents) 6. 0%
April%: 60%
June%: 100%
Build template for GECARS-FDL projects in RACES
Description: Document technical steps required to implement GECARS LITE for RACES ERP, based on Onshore Wind Mexico project.
M1. gather current technical plan from project team M2. validate with each group the tasks and the timings M3. pilot during Mexico UAT in May M4. publish the template with stakeholders
Today %: 5%
April %: 50%
June %: 100%
Work on monthly close initiative
Description: Close 2 gaps assigned to DT for ONW APAC(PBPC)
Milestone: TBD
Character count = 0/1,000
GE Volunteer Community
Description: Take ownership of modules under GE VOLUNTEER COMMUNITY. Teach students JAVA/ALGORITHM, Hands on coding across multiple session.
M1: Conduct atleast 1 session by April
M2: Conduct atleast 2 sessions by June
Today%: 0%
April%: 50%
June%: 100%
Participate in Lean event
Description: Take part in atleast two lean events, to understand the process followed and to develop the lean mindset.
M1: One lean event by April
M2: Two lean events by June
Today%: 50%
April%: 50%
June%: 100%
Self learning
Description: Study the lean courses and try to adapt them in daily workflow.
M1: Lean learning (JAN-FEB)
M2: Failure to flow (Mar)
M3: Problem solving (May)
Today%: 30% ( M1 done)
April%: 60%
June%: 100%
Networking and building relations
Description: Build network in and beyond GE Renewable Energy DT, build strong relations with other teams in GE REN DT across course of internship.