## Project Plan_ONW Mexico
Steps# | Lite Integration - Tasks & Activities | Description | Assigned To | Duration | Start Date | End Date | % Complete | Status | Comments
1 | Kick off and Project Initiation |  |  | 1D
2 | Requirements
2.1 | Functional Due Diligence (Cash + Collections) | Finalize Oprations strategy and the servicing scope | Genpact
2.2 | IT Due Diligence | Finalise GENAISYS configuration based on business needs | Genpact IT
2.3 | Races Requirements | Clarify with Anett | Races IT
2.4 | FDL Requirements | Clarify with Andy/Helen | FDL team
3 | Design and Build (Pre-requisite to SIT) |  |  | 5D
3.1 | Setups at GENAISYS | Configure and prep GENAISYS to perform testing | Genpact IT
3.2 | Setups at Races | Clarify with Anett Setup Receipts Methods in RACES | Races IT
3.3 | Connectivity and setup between FDL and Races | Clarify with Andy/Helen (need substep) Takeaway - Connectivity shud exist between FDl and Races. Expected customer and invoice data to be available in FDL | FDL Team
3.3.1 | Point the connection as per preferred instance | FDL instance and Races instance to be decided and FDL instance points to Races instance | HVR Team
3.3.2 | Modify in FDL the security for the GECARS interface user to include additional Org Ids |  | FDL Team
3.3.3 | Mirror refresh for all modules including Receipts table |  | FDL Team
3.3.4 | Model refresh for all modules including Receipts table | Data shud be in Races for model refresh | FDL Team
3.4 | FDL interface setup with GENAISYS | Establish/Check FDL instance connectivity with GENAISYS test SFTP server | Genpact IT
3.5 | Rifle shot test to confirm connectivity in the agreed environment for testing (FDL-> GENAISYS) | Optional step to check the instances are connected essentially FDL to GENAISYS. To make sure that on sending data feed during testing, it doesn’t fail | FDL Team, Genpact IT
3.6 | Identify Cash Applier & get required access to Races test environment | Users Readiness in RACES | Genpact Cash
3.7 | Prepare Cash Application scenario for Cash App Testing | Prepare cash test script | Genpact Cash
4 | Testing - SIT Execution |  |  | 10D
4.1 | Lite Integration Testing Day - 0
4.1.1 | FDL Refresh - Initial load | Clarify with Andy/Helen Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
4.1.2 | FDL to send Customer feed to GENAISYS
4.1.3 | FDL to send Invoice feed to GENAISYS
4.1.4 | GENAISYS to load the customer & invoice feed |  | Genpact IT
4.1.5 | Validation of customer & invoice feed in GENAISYS | Manual Recon between GENAISYS & RACES Customer Master & OI Report | Genpact
4.1.6 | Prepare Cash Test Scenarios for Day 1 & 2 | Update Cash Test scenarios with accurate Inv#, CN# and Customer# | Genpact Cash
4.2 | Lite Integration Testing Day - 1
4.2.1 | Cash Application Test at Races - Day 1 scenarios |  | Genpact Cash Applier
4.2.2 | FDL Refresh | Clarify with Andy/Helen Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
4.2.3 | FDL to send Customer feed to GENAISYS
4.2.4 | FDL to send Invoice feed to GENAISYS
4.2.5 | GENAISYS to load the customer & invoice feed |  | Genpact IT
4.2.6 | Validation of customer & invoice feed in GENAISYS | 1. Manual Recon between GENAISYS & RACES Customer Master & OI Report 2. Validation of Cash App Testing Results | Genpact 1 - Collections 2 - Cash
4.3 | Lite Integration Testing Day - 2
4.3.1 | Cash Application Test at Races - Day 2 scenarios |  | Genpact Cash Applier
4.3.2 | FDL Refresh | Clarify with Andy/Helen Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
4.3.3 | FDL to send Customer feed to GENAISYS
4.3.4 | FDL to send Invoice feed to GENAISYS
4.3.5 | GENAISYS to load the customer & invoice feed |  | Genpact IT
4.3.6 | Validation of customer & invoice feed in GENAISYS | 1. Manual Recon between GENAISYS & RACES Customer Master & OI Report 2. Validation of Cash App Testing Results | Genpact 1 - Collections 2 - Cash
4.4 | SIT Sign off |  | Genpact Races
5 | Design and Build (Pre-requisite to UAT) |  |  | 5D
5.1 | Setups at GENAISYS | Configure and prep GENAISYS to perform testing | Genpact IT
5.2 | Setups at Races | Clarify with Anett Setup Receipts Methods in RACES | Races IT
5.3 | Connectivity and setup between FDL and Races | Clarify with Andy/Helen (need substep) Takeaway - Connectivity shud exist between FDl and Races. Expected customer and invoice data to be available in FDL | FDL Team
5.3.1 | Point the connection as per preferred instance | FDL instance and Races instance to be decided and FDL instance points to Races instance | HVR Team
5.3.2 | Modify in FDL the security for the GECARS interface user to include additional Org Ids |  | FDL Team
5.3.3 | Mirror refresh for all modules including Receipts table |  | FDL Team
5.3.4 | Model refresh for all modules including Receipts table | Data shud be in Races for model refresh | FDL Team
5.4 | FDL interface setup with GENAISYS | Establish/Check FDL instance connectivity with GENAISYS test SFTP server | Genpact IT
5.4 | Rifle shot test to confirm connectivity in the agreed environment for testing (FDL-> GENAISYS) | Optional step to check the instances are connected essentially FDL to GENAISYS. To make sure that on sending data feed during testing, it doesn’t fail | FDL Team, Genpact IT
5.4 | Identify Cash Applier & get required access to Races test environment | Users Readiness in RACES | Genpact Cash
5.4 | Prepare Cash Application scenario for Cash App Testing | Prepare cash test script | Genpact Cash
6 | Testing - UAT Execution |  |  | 10D
6.1 | Lite Integration Testing Day - 0
6.1.1 | FDL Refresh - Initial load | Clarify with Andy/Helen Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
6.1.2 | FDL to send Customer feed to GENAISYS
6.1.3 | FDL to send Invoice feed to GENAISYS
6.1.4 | GENAISYS to load the customer & invoice feed |  | Genpact IT
6.1.5 | Validation of customer & invoice feed in GENAISYS | Manual Recon between GENAISYS & RACES Customer Master & OI Report | Genpact
6.1.6 | Prepare Cash Test Scenarios for Day 1 & 2 | Update Cash Test scenarios with accurate Inv#, CN# and Customer# | Genpact Cash
6.2 | Lite Integration Testing Day - 1
6.2.1 | Cash Application Test at Races - Day 1 scenarios |  | Genpact Cash Applier
6.2.2 | FDL Refresh | Clarify with Andy/Helen Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
6.2.3 | FDL to send Customer feed to GENAISYS
6.2.4 | FDL to send Invoice feed to GENAISYS
6.2.5 | GENAISYS to load the customer & invoice feed |  | Genpact IT
6.2.6 | Validation of customer & invoice feed in GENAISYS | 1. Manual Recon between GENAISYS & RACES Customer Master & OI Report 2. Validation of Cash App Testing Results | Genpact 1 - Collections 2 - Cash
6.3 | Lite Integration Testing Day - 2
6.3.1 | Cash Application Test at Races - Day 2 scenarios |  | Genpact Cash Applier
6.3.2 | FDL Refresh | Clarify with Andy/Helen Refresh FDL mirror and model, all modules (incl. Receipts table) | FDL Team
6.3.3 | FDL to send Customer feed to GENAISYS
6.3.4 | FDL to send Invoice feed to GENAISYS
6.3.5 | GENAISYS to load the customer & invoice feed |  | Genpact IT
6.3.6 | Validation of customer & invoice feed in GENAISYS | 1. Manual Recon between GENAISYS & RACES Customer Master & OI Report 2. Validation of Cash App Testing Results | Genpact 1 - Collections 2 - Cash
6.4 | UAT Sign off |  | Genpact Races
7 | Go-No Go Review |  | Genpact | 1D
8 | CCB Approval |  | Races IT | 1D
9 | Cutover |  |  | 5D
9.1 | Raise Races access for Cash Applier & Collector |  | Genpact
9.2 | Users Training for Cash Ops and Collections, if required |  | Genpact
9.3 | Setups at Races |  | Races IT
9.4 | Setups at FDL |  | FDL Team
9.5 | Setups at GENAISYS |  | Genpact IT
10 | Go - Live
11 | Deploy eReports & grant access to required users |  | Genpact IT | 10D
12 | Hypercare