## Workout Template
| When |  | Where |  |  |  | What |  | Why
Issue # | Start | End | System & Tools | Process Frames | Category | Resources & Know How | Defect/Effort Type | Rule impacted | Cause (Suggested 5W) | Solution | Responsible | Accountable | Consulted | Informed | Comments / Roadblock | Benefit | Impact Low/High | Effort Low/High | Dependency / Help need | Time saving | # items based on January analysis
K1 |  |  | Auto Bank | Conversion table data | System | N/A | "Customer Name to Cust Number" missing in conversion table - No customer identification by Auto Bank | CICL_CNAME_CNUMBER | New customer same customer changed bank narration different bank account used by customer | 1) Analyze and update Table (Serrala use business partner, BSEG, FBL5N0) | Nobin |  | AML, Serrala |  | Manual work, time constraint. | Customer identification | High | High |  |  | 266 Total Name and IBAN updates
[5 empty] | System |  |  |  |  | 2) Check auto update option from PP screen & confirm update process with AML team | Cash applier |  | AML, Serrala |  |  | Customer identification | High | Low
K2 |  |  | Auto Bank | Conversion table data | System | N/A | IBAN to customer number missing in table - No customer identification by Auto Bank. | CICL_IBAN_CNUMBER | New conversion table | 1) Analyze and update Table (Serrala use business partner, BSEG, FBL5N0) |  |  | AML, Serrala |  |  | Customer identification | High | High |  |  | 266 Total Name and IBAN updates
[5 empty] | System |  |  |  |  | 2) Use Sending bank details Table (MICR, IBAN) auto update |  |  | AML, Serrala |  | Need to confirm bank file format in Partner bank details IBAN field | Customer identification | High | Low
K3 |  |  | TRAX | Bank Statement Extraction | Data | N/A | Incomplete, not readable or missing bank narration | All AR Rules | Format bank file Format conversion issue Character limitation 360 Incorrect Customer input- free field, not mandatory, abbreviations, incorrect invoice number Language issue (chinese ) Special character issue "? " " space" //\\ | -Change format from MT940 to BAI/CAMT53 from TRAX to Altais (character limit approx. 4000) | [5 empty] | All characters provided by Bank available in Auto Bank | High | High | Business Treasury Approval and Budget requireed |  | total 29
[5 empty] | Customer input |  |  |  |  | -Educate Customers to use correct format/ information/ abbreviation - top 10 customers first | [6 empty] | High | High |  |  | total 29
[5 empty] | System |  |  |  |  | - Space removing in Bank file narration in Auto bank |  |  | Serrala |  |  |  | Low | TBD |  |  | total 29
K4 |  |  | TRAX | Bank Statement Extraction | Data | N/A | Issues converting CAMT53 to MT940 in TRAX - missing line description. | All AR Rules | -TRAX limitation to translate CAMT53 line description into MT940 -Truncation issue >360 character -Many banks globally will move to CAMT53 | 1) TRAX fix ready to deploy in March, but 360 limitation will remain for MT940 format. 2) Change format from MT940 to BAI/CAMT53 from TRAX to Altais | [6 empty] | High | High | Business Treasury Approval and Budget requireed |  | 0
K5 |  |  | TRAX | Bank Statement Extraction | Data | N/A | Truncation issue with MT940 > 360 characters for CAMT53 and BAI files which are translated by TRAX to MT940 for ERP feed. | All AR Rules | -BAI (and CAMT) are translated to MT940 by TRAX - but MT940 has a max character limit of 360: all characted >360 are cut off. -MT940 is a global standard format -Customers are able to put in more characters in bank narration | Investigate changin Feed options from TRAX to ERP: 1) Change all file format for ERP feed from MT940 to BAI or CSV 2) Multiple file format flow: CAMT53 to CAMT53 and BAI to BAI and keep MT940 for the rest. |  |  |  |  | Confirm if Auto Bank can handle CAMT file format. |  | High | High | Business Treasury Approval and Budget requireed |  | 12
K6 |  |  | TRAX, SAP, Auto Bank | Bank Statement Extraction | Data | N/A | Bank sends file to Web cash, which does not convert Chinese character to English very well. | All AR Rules | -Language issue (chinese ) -Chinese customers use Local Banks with remittance info in Chinese - converted data in TRAX to English. -Chinese Character needed to ID the customer - English character can not give unique customer -Altais customer setup in Chinese (need to clarify) | Investigate Chinese Character options in Altais and Auto Bank | [6 empty] | High | High |  |  | 123
K7 |  |  | TRAX | Bank Statement Extraction | Data | N/A | Information regarding VAT, GST, rebate, service charge, misc. expenses etc., not provided in bank description due to which payment doesn’t get applied automatically | CICL_INV_INCL_CHGS | -Customer did not provide info in the bank narration -Bank does not provide info | -Confirm if this is bank dependant - contact Bank | [6 empty] | Low | Low |  |  | 66
K8 |  |  | Remit Library, OCR | Remittance Extraction | Process | N/A | Remittance information not received or received late | CICL_INTGR_REMI | -Customer not providing remittance at all or sending after the payment was made -Customer sending remittance to incorrect 'place' (collections, bank , business) -Customer not aware of where to send remittance; Invoice templates do not show remittance library email-address -Remittances received at different place (Collections, Cash, PM, Biz) are not forwarded to Remit Libary -Remittance upload cycle time -other shared mailboxes in use from Business side where remittance is sent by customers (need autoforward) | -Auto forward rule from other mailbox to Renewables global one -Educate Biz/Collections/Cash to forward | [6 empty] | High | High |  |  | total remittance defects: 170
[5 empty] | Customer input |  |  |  |  | Educate Customer to send remittance to the correct email box - remit library. Add email address in Collector email signature. |  |  |  |  | How to we measure the success? What is the control? Lack of capability to measure cycle time |  | High | High |  |  | total remittance defects: 170
[5 empty] | Process |  |  |  |  | Invoice templates to be validated and updated with correct email address for Renewables. |  |  |  |  | Changing Invoice templates is complex process |  | High | High |  |  | total remittance defects: 170
K9 |  |  | Remit Library, OCR | Remittance Extraction | Customer input | N/A | Remittance information incomplete or not readable by OCR | CICL_INTGR_REMI | -special character -Chinese character -abbreviations -incorrect invoice numbers -OCR is converting remit in pdf - landscape remit is changed in portait and information is truncated (smarteye) -OCR not able to read screenshot | -Educate Customers to use correct format/ information/ abbreviation - top 10 customers first |  |  |  |  | No Visibility at payment level No tracking possible on bank feed or customer input |  | High | High |  |  | total remittance defects: 170
[5 empty] | System |  |  |  |  | -Technical fixes in OCR translation (chinese, special character, truncation) |  |  | Serrala |  |  |  | High | TBD |  |  | total remittance defects: 170
K10 |  |  | SAP | Clearing invoices | System | N/A | Tolerance limit for automation of small amount write off |  | -User (0.01 USD) and coco (1USD) tolerance limits in SAP are not in line | Adjust user and coco tolerance limits in SAP to be in sink | [6 empty] | Low | Low | IT support |  | no data
K11 |  |  | Auto Bank | Clearing invoices | Process | N/A | No Partial payment Automation setup in Auto Bank causing manual application for all types of underpayment even if invoice and customer are identified | Underpayment Rule (NEW) | -Underpayment rule was not in scope until now -Different types of underpayment (complexity of booking) discount, VAT, WHT, dispute -SAP standard requirements for certain type of underpayments -Business and Process requirement; no standard approach -coco specifics | Rule created in test environment, however still waiting for tolerance limit raise in the SAP (related to point# 6) | [6 empty] | High | High | Business, IT, Serrala |  | 5
K12 |  |  | TRAX, Auto Bank | Customer identification / Clearing invoices | Data | N/A | Invoice number contains special character (?, space) or additional number within the invoice number due to which system is unable to identify invoice number | CICL_STANDARD CICL_INTGR_REMI CICL_INV_INCL_CHGS | -Customer AP department uses special character / handwritten characters on remittance/scan -Bank translation issues? - not TRAX issue | Investigate in Auto Bank | [6 empty] | High | High | Serrala/IT support |  | 59
K13 |  |  | Auto Bank, SAP | Clearing invoices | System | N/A | Down Payments not auto posted as Auto Bank cannot pick invoice tax code from DB type invoices and post it on bank line item | Down Payment Rule (NEW) | -Auto Bank cannot pick invoice tax code from DB type invoices and post it on bank line item -different tax codes per invoice/customer depending on the country | SAP fix to be investigated. | [6 empty] | Low | High | Serrala/IT support |  | 8
K14 |  |  | Auto Bank, Bank | Clearing invoices | Data | N/A | Lockbox payments for checks in NAM are manually booked by cash applier | GICL_LOCKBOX_CHECKS | -Bank issue with the BAI file -low volume of check payments 40 lines per month 20% of AR # - | Implement BAI2 file load for lockboxes. |  |  |  |  | due to Low volume of items per LB line this has remain a manual process |  | Low | High | Bank |  | 15 Lockbox line items
K15 |  |  | Auto Bank, SAP | Clearing invoices | System | N/A | WBS information not filled in on payment line by Auto Bank for auto and manual posting. Business project reporting requirement. | N/A | -Assigment field save option in PP screen was never activated - is possible since Upgrade for 1 payment for 1 WBS -Auto posting is not picking up the WBS in the payment line - enhancement made by Serrala which is in testing mode.(1 WBS) -Splitting of payment in multiple WBS is not possible in Auto Bank. | Fix for 1 WBS scenarios in Auto Bank. Payment split in >1 WBS require manual workaround via GL |  |  |  |  | split payment for multiple WBS cannot be fixed and will remain manual workaround; <10% of cases. Need to asses what is the impact of WBS on autoapplied items today that will fail due to this scenario | WBS entered on payment line | Low | High | Serrala/Business |  | all items
K16 |  |  | Auto Bank, SAP | Clearing invoices | System | N/A | Cross coco application fails in case of on account postings and postings to multiple coco/customer | CICL_INTGR_REMI CICL_STANDARD CICL_INV_INCL_CHGS | -"cross coco handshake GL account" is failing at the backend with posting through auto bank -OBYA settings in SAP standard to be confirmed | Identify required Fix in Auto Bank or SAP | [6 empty] | Low | TBD | Serrala/IT |  | 0
K17 |  |  | Auto Bank | non-AR identification | Process | N/A | I2C Cash team spending time on moving non-AR items from PP screen to xx1 GL with Suspense rule for incoming payments. This also includes bank accounts with only non-AR activity which were never part of their scope. | GIOA_SUSPENSE | -This rule is is set as 'post processing' -non-AR rules for incoming cash not set up; no unique identifiers -no AR vs non-AR bank accounts -access to PP screen for I2C cash applier | new rules on non_AR incoming |  |  |  |  | Not all no-AR can be automated - if no identifier |  | High | High | R2R |  | total January all coco (menat excluded): 586
K18 |  |  | WebCash, Autobank | Bank Statement Extraction | Process | Key User | Daily Validation of Web Cash vs Auto Bank by Key Users is manual. (lean opportunity) | N/A | -manual process -misses in bank statement loading to be resolved same day | Program to automate this validation | [6 empty] | Low | High |  |  | Manual effort: 30 min per day
K19 |  |  | Auto Bank, Bank | Clearing invoices | Customer input |  | Misdirected Cash - Cash paid to wrong bank account. Invoice cannot be applied due to wrong coco posting | GIOA_SUSPENSE | -wrong bank info on invoice -customer dealing with 2 different BU - using 1 bank acocunt for all payments -bank account changed and not updated in AP system | Ask Customer to change payment behaviour | [6 empty] | Low | Low | Customer |  | no data
K20 |  |  | Auto Bank, Bank | Clearing invoices | Process |  | Letter of Credit payments are always manually applied | CICL_INTGR_REMI CICL_STANDARD CICL_INV_INCL_CHGS | -no bank details for LC payments in the bank description -need LC copy to be able to apply -bank charges deducted from payment | Check if we can use OCR to match the payment | [6 empty] | Low | High | Bank, Treasury
K21 |  |  | Remit Library, OCR | Remittance Extraction | System | N/A | Remittance information not found by Rule due to deduction of bank charge from amount of payment. Or decimal not considered in rule. | CICL_INTGR_REMI | -Smarteye search on total amount in Remittance and currency and save remittance with this payment amount. -rebate, short payment -OCR only matching on the basis of total payment amount - not on customer name | [7 empty] | Low | High | Serrala |  | no data
K22 |  |  | Remit Library, OCR | Remittance Extraction | System | N/A | OCR not able to recognize remittance amount for multiple invoice payment. | CICL_INTGR_REMI | -key words like 'total amount',' total payment', 'net amount' are needed to be able to identify multiple payment remittance. | [7 empty] | High | High | Serrala |  | no data
K23 |  |  | Auto Bank, SAP | Clearing invoices | System | N/A | Limitation of AB to meet ABM principles: Selection of multiple invoices not in sequence of PD date | CICL_CNAME_CNUMBER CICL_IBAN_CNUMBER | -auto bank cannot read SP codes -auto bank cannot make a random selection out of (PD) invoices -auto bank will only search in 1 customer account with that name | [7 empty] | Low | TBD | Serrala |  | no data
K24 |  |  | Auto Bank | Clearing invoices | System | N/A | Payment for multiple customer accounts will fail. Name to Number rule will only be able to apply the payment in 1 customer account | CICL_CNAME_CNUMBER | conversion table is only able to link name to 1 customer number | [7 empty] | Low | TBD | Serrala |  | 12
K25 |  |  | Auto Bank | Clearing invoices | System | N/A | Auto Bank not able read partail invoice number. Missing start identifier | CICL_INTGR_REMI CICL_STANDARD CICL_INV_INCL_CHGS | invoice sequence in rule based on starting identifier like 7000*** | [7 empty] | Low | Low | Serrala |  | no data
K26 |  |  | Auto Bank FS2 | Analytics Automation rates | Process | N/A | AR Auto cash rate Analysis | All AR Rules | -TOOL: FS2 implemented in Jan'21 -DATA: lack of transactional data line by line to identify the real rootcause of manual application -PEOPLE: need to design consistent and comprehensive process for analysis and action execution. R & R for Key users to be redefined. | [7 empty] | High | High |  |  | N/A
K27 |  |  | Auto Bank | Clearing invoices | Process | N/A | Menat region reversal of Auto applied items and all AR booked outside of Auto Bank manual | All AR Rules | WBS | [7 empty] | High | High |  |  | Turkey/India/Menat: 685 AR paymets in Jan
K28 |  |  | Auto Bank | Clearing invoices | Process | N/A | India and Turkey on Auto Bank "light" - all AR reclassed to xx1 and booked manual to S/L -> 0% automation | All AR Rules | [8 empty] | High | High |  |  | Turkey/India/Menat: 685 AR paymets in Jan
Note on R2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Impact on identified Defect

## Actions
# | Defect | Solution | ACTION | Owner | Timeline
1
2
3